## Sheet1
# | isDone | Task | Milestone | Priority | Bug / Feature | Difficulty | Date added | Reported by | Related Object | Score | Notes
|  | Open tasks: 29 | [7 empty] | *
1 |  | Stop SPCM counter when scan starts. | 2 | 4 | Feature | 3 | 2017-10-31 | Nadav | Stage, SpacmCounter | 1 | Perhaps by introducing Const property to ClassStage, EVENT_ABOUT_TO_SCAN?
2 | TRUE | Find a way to externally update ViewStageScanParams |  | 7 | Bug | 2 | 2017-10-31 | Nadav | ViewStageScanParams |  | Eventually, told stage to report that it has updated itself
3 |  | Find out why C-867 (PI686) might not be an active object simetimes | 2 | 6 | Bug | 4 | 2017-10-31 | Nadav | Stage | 2.4 | It is still active, and needs disconnecting, but its ID is not saved
4 | TRUE | Implement Class DataCursor for ease of use. |  | 2 | Feature | 2 | 2017-11-06 | Nadav | ViewImageResultPanelCursor
5 |  | Fix Colorbar | 2 | 3 | Partly, a bug | 3 | 2017-11-06 | Nadav | ViewImageResultImage, ViewImageResultPanelColormap | 0.75 | Requires saving its axes, if exist, as a property
6 |  | MAJOR BUG: initating an object twice (sometimes?) calls the destructor for both old and new object | 2 | 4 | Bug | 5 | 2017-10-01 | Re'em & Nadav | BaseObject, SpcmCounter? | 1.3333 | It used to happen with SPCM, as far as Nadav can remember
7 |  | Implement Experiment class | 3 | 10 | Feature | 5 | A long time ago | Yoav | Experiment | 1.6667
8 | TRUE | Fix Marker text |  | 8 | Bug | 3 | 2017-11-05 | Nadav | ViewImageResultPanelCursor
9 | TRUE | Create MoveTo cursor |  | 10 | Feature | 3 | 2017-11-05 | Nadav | ViewImageResultPanelCursor
10 |  | Fix SPCM's ScanByLine | 1 | 10 | Bug | 4 | 2017-11-06 | Nadav | NiDaqControlledSpcm | 4
11 |  | Implement formatting and removal of trailing zeros for all position editBox'es | 1 | 2 | Bug | 1 | 2017-11-06 | Nadav | StringHelper | 2
12 |  | Rewrite algorithm for detecting and warning about tilt correction | 2 | 2 | Feature | 3 | 2017-11-05 | Nadav | Stage, ViewStagePanelTiltCorrection | 0.5 | It works fine, for now, but there is redundancy in the code, due to work by both Yoav and Re'em
13 | TRUE | Cursor zoom should update scan parameters |  | 3 | Bug | 3 | 2017-11-06 | Nadav | ViewImageResultPanelCursor, StageScanParams |  | Probably will be solved by solving #2
14 | TRUE | Fix todo list |  | 10 | Bug | 5 | 2017-11-05 | Yoav | xlsx
15 |  | Create bug update form | 2 | 1.5 | Feature | 2 | 2017-11-06 | Nadav | xlsx | 0.5 | Probably use google sheets. Priority = {1:5} + 3 Difficulty = 3 automatically
16 |  | Consider what happens if one instance of SPCM counter closes and there are others still open | 2 | 2 | Feature | 2.5 | 2017-11-06 | Nadav | ViewSpcmCounter | 0.57143 | If required, could use static variable which counts instances
17 |  | implement Joystick | 2 | 2 | Feature | 1 | 2017-11-05 | Nadav | ViewStagePanelMovementControl | 1
18 | TRUE | Look into cursor type |  | 1 | Feature | 1.5 | 2017-11-05 | Nadav | ViewImageResultPanelCursor
19 | 0.5 | Remove disconnect function from ViewMainImage. Implement GUI for disconnection in the future | 2 | 3 | Feature | 1 | 2017-10-01 | Nadav | ViewMainImage | 0.75
20 | FALSE | Push This week's commits |  | 10 | Feature | 1 | 2017-11-06 | Nadav | Git | 5 | 2017-11-19
21 |  | Consider what happens if one instance of SPCM counter is stopped by debugging | 2 | 2 | Bug | 4 | 2017-10-01 | Nadav | ViewSpcmCounter | 0.8
22 |  | What happens when Daq sends error? | 2 | 3 | Bug | 3 | 2017-10-01 | Nadav | NiDaq | 1.5 | Should probably reset and send event
23 |  | Fix size bug for main image view | 2 | 4 | Bug | 4 | 2017-10-01 | Nadav | ViewMainImage | 1.6
24 |  | marker is deleted when new line in scan occurs. | 2 | 2 | Bug | 1.5 | 2017-11-06 | Nadav | ViewImageResultPanelCursor, ViewImageResultImage | 1.6 | if important, solution probably needs to be made using vAxes.NextPlot = 'replacechildren'; Yoav: nice to have, not critical, don't kill youself
25 |  | Disable option to use axis equal for 1d plot. | 2 | 1 | Bug | 3 | 2017-11-07 | Nadav | ViewImageResultPanelPlot | 0.5
26 |  | If "from" and "to" are identical, output warning | 2 | 2 | Feature | 2 | 2017-11-07 | Nadav | ViewStageScanParams | 0.66667
27 | TRUE | Auto-set marker when clicking scan or loading image | 1 | 5 | Bug | 3 | 2017-11-02 | Nadav | ViewImageResultPanelCursor, ViewImageResultImage |  | probably needs object that saves dimensinality of current figure
28 | TRUE | StageScanner, lines 111-114. Look into Them. They are probably redundant | 1 | 5 |  |  | 2017-11-07 | Nadav | StageScanner
29 |  | Unify stages 686 & 501 | 1 | 6 | Feature | 1.5 | 2017-11-05 | Nadav | ClassPIM686, ClassPIM501 | 2.4
30 |  | "last file is loaded - no possible next" | 2 | 2 | Feature | 3 | 2017-11-12 | Nadav | SaveLoad | 0.5 | Also: previous. Re'em was aware of this problem #OneDay
31 | TRUE | Add counter of open tasks | 2 | 1 | Feature | 3 | 2017-11-15 | Nadav | xlsx
32 |  | Implement stage and lasers for setup 1 | 1.5 | 5 | Feature | 3 | 2017-11-16 | Yoav |  | 1.25
33 |  | Implement stage and lasers for setup 3 | 1.5 | 5 | Feature | 3 | 2017-11-16 | Yoav |  | 1.25
34 |  | Change errorbars in SPCM counter to polygon | 2 | 2 | Feature | 4 | 2017-10-01 | Nadav | AxisHelper | 0.4
35 |  | Add scale (1um bar) to image | 2 | 1 | Feature | 2 | 2017-10-01 | Nadav | AxisHelper | 0.33333
36 | TRUE | Make Panel cursor event listener to event sendEventImageUpdated | 1 |  | Feature |  | 2017-11-16 | Nadav
37 |  | When scanning, disable (grey out) all movement related buttons (also cursor panel and joystick) | 2 |  | Feature |  | 2017-11-16 | Yoav | StageScanner, ViewStagePanel… | 0 | Listen to events of scanning starting and stopping
38 |  | Implement Tracker | 1.5 |  | Feature |  | 2017-11-16 | Yoav | Tracker | 0
39 |  | Create ImageResultAxes that other objects will refer to (BaseObject), and it will be placed inside ViewImageResultImage | 2 | 3 | Feature | 2 | 2017-11-19 | Yoav | ImageResultAxes, ViewImageResultImage, ViewImageResultPanelCursor, ViewImageResultPanelPlot, ViewImageResultPanelColormap | 1 | By that, ViewImageResultImage will no longer be a base object, and this will remove the need to
39 |  | Implement SetLocationFromCursor also for 1D | 2 | 2 | Bug | 3 | 2017-11-19 | Nadav | DataCursor | 1
Formulas:
isDone = DAYS(Table2[[#This Row],[Notes]],TODAY())>0 + N("Computes whether or not it is time to routinely commit to git")
Note on E1: Author: 1--10
Note on G1: Author: 1--5
Note on K1: Author: = Priority * (1 + ~Feature) * (1-isDone) /Difficulty) More verbally: It shows only if there is an open task, and computes the formula, as long as the task is not done.
Note on L22: Author: Next github commit deadline