## Sheet1
# | isDone | Task | Priority | Bug / Feature | Difficulty | Date added | Reported by | Related Object | Score | Notes
1 |  | Stop SPCM counter when scan starts. | 4 | Feature | 3 | 2017-10-31 | Nadav | Stage, SpacmCounter | 1 | Perhaps by introducing Const property to ClassStage, EVENT_ABOUT_TO_SCAN?
2 |  | Find a way to externally update ViewStageScanParams | 7 | Bug | 2 | 2017-10-31 | Nadav | ViewStageScanParams | 4.6667 | Either by making it an EventSender or finding method which does it already
3 |  | Find out why C-867 (PI686) might not be an active object simetimes | 6 | Bug | 4 | 2017-10-31 | Nadav | Stage | 2.4 | It is still active, and needs disconnecting, but its ID is not saved
4 |  | Implement Class DataCursor for ease of use. | 2 | Feature | 2 | 2017-11-06 | Nadav | ViewImageResultPanelCursor | 0.66667
5 |  | Fix Colorbar | 3 | Partly, a bug | 3 | 2017-11-06 | Nadav | ViewImageResultImage, ViewImageResultPanelColormap | 0.75 | Requires saving its axes, if exist, as a property
6 |  | MAJOR BUG: initating an object twice (sometimes?) calls the destructor for both old and new object | 4 | Bug | 5 | 2017-10-01 | Re'em & Nadav | BaseObject, SpcmCounter? | 1.3333 | It used to happen with SPCM, as far as Nadav can remember
7 |  | Implement Experiment class | 5 | Feature | 5 | A long time ago | Yoav | Experiment | 0.83333
8 |  | Fix Marker text | 8 | Bug | 3 | 2017-11-05 | Nadav | ViewImageResultPanelCursor | 4
9 |  | Create MoveTo cursor | 8 | Feature | 3 | 2017-11-05 | Nadav | ViewImageResultPanelCursor | 2
10 |  | Fix SPCM's ScanByLine | 7 | Bug | 4 | 2017-11-06 | Nadav | NiDaqControlledSpcm | 2.8
11 |  | Implement formatting and removal of trailing zeros for all position editBox'es | 2 | Bug | 1 | 2017-11-06 | Nadav | StringHelper | 2
12 |  | Rewrite algorithm for detecting and warning about tilt correction | 2 | Feature | 3 | 2017-11-05 | Nadav | Stage, ViewStagePanelTiltCorrection | 0.5 | It works fine, for now, but there is redundancy in the code, due to work by both Yoav and Re'em
13 |  | Cursor zoom should update scan parameters | 3 | Bug | 3 | 2017-11-06 | Nadav | ViewImageResultPanelCursor, StageScanParams | 1.5 | Probably will be solved by solving #2
14 | 1 | Fix todo list | 10 | Bug | 5 | 2017-11-05 | Yoav | xlsx
15 |  | Create bug update form | 1.5 | Feature | 2 | 2017-11-06 | Nadav | xlsx | 0.5 | Probably use google sheets. Priority = {1:5} + 3 Difficulty = 3 automatically
16 |  | Consider what happens if one instance of SPCM counter closes and there are others still open | 2 | Feature | 2.5 | 2017-11-06 | Nadav | ViewSpcmCounter | 0.57143 | If required, could use static variable which counts instances
17 |  | implement JoyStick | 2 | Feature | 1 | 2017-11-05 | Nadav | ViewStagePanelMovementControl | 1
18 |  | Look into cursor type | 1 | Feature | 1.5 | 2017-11-05 | Nadav | ViewImageResultPanelCursor | 0.4
19 | 0.5 | Remove disconnect function from ViewMainImage. Implement GUI for disconnection in the future | 3 | Feature | 1 | 2017-10-01 | Nadav | ViewMainImage | 0.75
20 |  | Push This week's commits | 8 | Feature | 1 | 2017-11-06 | Nadav | Git | 4
21 |  | Consider what happens if one instance of SPCM counter is stopped by debugging | 2 | Bug | 4 | 2017-10-01 | Nadav | ViewSpcmCounter | 0.8
22 |  | What happens when Daq sends error? | 3 | Bug | 3 | 2017-10-01 | Nadav | NiDaq | 1.5 | Should probably reset and send event
Note on D1: Author: 1--10
Note on F1: Author: 1--5
Note on J1: Author: = Priority * (1 + ~Feature) * (1-isDone) /Difficulty) More technically: It shows only if there is an open task, and computes the formula, as long as the task is not done.