## Sheet1
# | isDone | Task | Milestone | Priority | Bug / Feature | Difficulty | Date added | Reported by | Related Object | Score | Notes
1 |  | Stop SPCM counter when scan starts. | 2 | 4 | Feature | 3 | 2017-10-31 | Nadav | Stage, SpacmCounter | 1 | Perhaps by introducing Const property to ClassStage, EVENT_ABOUT_TO_SCAN?
2 |  | Find a way to externally update ViewStageScanParams |  | 7 | Bug | 2 | 2017-10-31 | Nadav | ViewStageScanParams | 4.6667 | Either by making it an EventSender or finding method which does it already
3 |  | Find out why C-867 (PI686) might not be an active object simetimes |  | 6 | Bug | 4 | 2017-10-31 | Nadav | Stage | 2.4 | It is still active, and needs disconnecting, but its ID is not saved
4 |  | Implement Class DataCursor for ease of use. |  | 2 | Feature | 2 | 2017-11-06 | Nadav | ViewImageResultPanelCursor | 0.66667
5 |  | Fix Colorbar |  | 3 | Partly, a bug | 3 | 2017-11-06 | Nadav | ViewImageResultImage, ViewImageResultPanelColormap | 0.75 | Requires saving its axes, if exist, as a property
6 |  | MAJOR BUG: initating an object twice (sometimes?) calls the destructor for both old and new object |  | 4 | Bug | 5 | 2017-10-01 | Re'em & Nadav | BaseObject, SpcmCounter? | 1.3333 | It used to happen with SPCM, as far as Nadav can remember
7 |  | Implement Experiment class | 3 | 10 | Feature | 5 | A long time ago | Yoav | Experiment | 1.6667
8 | 1 | Fix Marker text |  | 8 | Bug | 3 | 2017-11-05 | Nadav | ViewImageResultPanelCursor
9 |  | Create MoveTo cursor |  | 10 | Feature | 3 | 2017-11-05 | Nadav | ViewImageResultPanelCursor | 2.5
10 |  | Fix SPCM's ScanByLine |  | 10 | Bug | 4 | 2017-11-06 | Nadav | NiDaqControlledSpcm | 4
11 |  | Implement formatting and removal of trailing zeros for all position editBox'es |  | 2 | Bug | 1 | 2017-11-06 | Nadav | StringHelper | 2
12 |  | Rewrite algorithm for detecting and warning about tilt correction |  | 2 | Feature | 3 | 2017-11-05 | Nadav | Stage, ViewStagePanelTiltCorrection | 0.5 | It works fine, for now, but there is redundancy in the code, due to work by both Yoav and Re'em
13 |  | Cursor zoom should update scan parameters |  | 3 | Bug | 3 | 2017-11-06 | Nadav | ViewImageResultPanelCursor, StageScanParams | 1.5 | Probably will be solved by solving #2
14 | 1 | Fix todo list |  | 10 | Bug | 5 | 2017-11-05 | Yoav | xlsx
15 |  | Create bug update form |  | 1.5 | Feature | 2 | 2017-11-06 | Nadav | xlsx | 0.5 | Probably use google sheets. Priority = {1:5} + 3 Difficulty = 3 automatically
16 |  | Consider what happens if one instance of SPCM counter closes and there are others still open |  | 2 | Feature | 2.5 | 2017-11-06 | Nadav | ViewSpcmCounter | 0.57143 | If required, could use static variable which counts instances
17 |  | implement Joystick |  | 2 | Feature | 1 | 2017-11-05 | Nadav | ViewStagePanelMovementControl | 1
18 |  | Look into cursor type |  | 1 | Feature | 1.5 | 2017-11-05 | Nadav | ViewImageResultPanelCursor | 0.4
19 | 0.5 | Remove disconnect function from ViewMainImage. Implement GUI for disconnection in the future |  | 3 | Feature | 1 | 2017-10-01 | Nadav | ViewMainImage | 0.75
20 | FALSE | Push This week's commits |  | 10 | Feature | 1 | 2017-11-06 | Nadav | Git | 5 | 2017-11-12
21 |  | Consider what happens if one instance of SPCM counter is stopped by debugging |  | 2 | Bug | 4 | 2017-10-01 | Nadav | ViewSpcmCounter | 0.8
22 |  | What happens when Daq sends error? |  | 3 | Bug | 3 | 2017-10-01 | Nadav | NiDaq | 1.5 | Should probably reset and send event
23 |  | Fix size bug for main image view |  | 4 | Bug | 4 | 2017-10-01 | Nadav | ViewMainImage | 1.6
24 |  | marker is deleted when new line in scan occurs. |  | 4 | Bug | 1.5 | 2017-11-06 | Nadav | ViewImageResultPanelCursor, ViewImageResultImage | 3.2 | if important, solution probably needs to be made using vAxes.NextPlot = 'replacechildren';
25 |  | Disable option to use axis equal for 1d plot. |  | 1 | Bug | 3 | 2017-11-07 | Nadav | ViewImageResultPanelPlot | 0.5
26 |  | If "from" and "to" are identical, output warning |  | 2 | Feature | 2 | 2017-11-07 | Nadav | ViewStageScanParams | 0.66667
27 |  | Auto-set marker after switch from 2D to 1D, and vice versa. |  | 5 | Bug | 3 | 2017-11-02 | Nadav | ViewImageResultPanelCursor, ViewImageResultImage | 2.5 | probably needs object that saves dimensinality of current figure
28 |  | StageScanner, lines 111-114. Look into Them. They are probably redundant |  |  |  |  | 2017-11-07 | Nadav | StageScanner | 10
29 |  | Unify stages 686 & 501 |  | 6 | Feature | 1.5 | 2017-11-05 | Nadav | ClassPIM686, ClassPIM501 | 2.4
30 |  | "last file is loaded - no possible next" |  | 2 | Feature | 3 | 2017-11-12 | Nadav | SaveLoad | 0.5 | Also: previous. Re'em was aware of this problem #OneDay
Formulas:
isDone = DAYS(Table2[[#This Row],[Notes]],TODAY())>0 + N("Computes whether or not it is time to routinely commit to git")
Note on E1: Author: 1--10
Note on G1: Author: 1--5
Note on K1: Author: = Priority * (1 + ~Feature) * (1-isDone) /Difficulty) More technically: It shows only if there is an open task, and computes the formula, as long as the task is not done.
Note on L21: Author: Next github commit deadline